## Shadowing Plan
Shadow Support Plan (4 Weeks) for 25 Applications Duration: 4 Weeks Objective: Lingaro support team shadows existing Capgemini team to observe live support operations,SOPs, Incidents & Tasks Handling, and prepare for reverse shadowing.
S.No | Objectivies
1 | Build complete operational understanding for all 25 applications.
2 | Observe and learn live ticket handling, monitoring, deployments, and change procedures.
3 | Capture cross-application dependencies, reporting, and escalation patterns.
4 | Prepare the team for independent handling in the Reverse Shadowing Phase.
Final Deliverables
1 | Shadow Support Tracker (Excel) – Daily entries and completion tracking | Lingaro Transition Manager
2 | Incident, Tasks & all SOP related Shadow activities Tracker- Daily | Capgemini Manager
3 | Co-ordinate and schedule all the meetings | Capgemini Manager
4 | Attend all meetings document and validate understanding of apps | Lingaro Support Members
5 | Risk Register | Lingaro Transition Manager
6 | Feedback Summary | Capgemini support team
7 | Feedback Forms-SME evaluation of Lingaro support Member readiness | Lingaro Transition Manager
8 | Daily Stand-up(30 min) | CG & Lingaro SMEs and PMs
9 | Weekly status reports to be shared with Edwin/Didier | Lingaro Transition Manager
10 | Documendation of other applications | Lingaro Support Members

## Shadow Support Tracker
No. | Application Name | Start Date | End Date | Incident Handling | Monitoring & Alerts | Change Mgmt | Problem Mgmt | Service Requests | Reporting & Metrics | Dependencies Review | SME Feedback (1–5) | % Complete | Status | Remarks
1 | App 1 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
2 | App 2 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
3 | App 3 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
4 | App 4 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
5 | App 5 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
6 | App 6 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
7 | App 7 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
8 | App 8 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
9 | App 9 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
10 | App 10 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
11 | App 11 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
12 | App 12 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
13 | App 13 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
14 | App 14 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
15 | App 15 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
16 | App 16 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
17 | App 17 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
18 | App 18 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
19 | App 19 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
20 | App 20 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
21 | App 21 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
22 | App 22 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
23 | App 23 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
24 | App 24 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending
25 | App 25 | 06-Oct-2025 | 25-Oct-2025 | [9 empty] | Pending

## Shadow Log
S.No | Date | Application Name | Ticket ID | Priority | Issue Description | Observed Action | Trainee Notes | Status | SME Verified